## Gantt Chart
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | WanderPaw | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Link-Leap | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Angela E. Corpuz | Project Start: |  | 2023-03-29
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Ivonne Glynn P. Lasco | Display Week: |  | 1 |  |  | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31
Rex-Imman H. Robles
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | Mary Gwen G. Susa | time axis 2023-03-27 to 2023-08-06
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2023-03-27 to 2023-08-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | INITIAL STAGE
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | PREPARATION | All Members | 100% | 2023-03-29 | 2023-04-17 | 20
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Brainstorm Concepts for an Application | All Members | 100% | 2023-03-29 | 2023-04-11 | 14
| Initial Project Proposal | All Members | 100% | 2023-04-12 | 2023-04-17 | 6
| Presentation of Initial Project Proposal | All Members | 100% | 2023-04-12 | 2023-04-12 | 1
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | STRUCTURE
| PROGRESS | All Members | 100% | 2023-05-07 | 2023-05-26
| Trello Workspace | Angela E. Corpuz | 100% | 2023-05-07 | 2023-05-07
| Github Repository | Angela E. Corpuz | 100% | 2023-05-07 | 2023-05-07
| Work Breakdown Repository | All Members | 100% | 2023-05-07 | 2023-05-26
| Gantt Chart | All Members | 95% | 2023-05-06 | 2023-05-26
| DESIGN | All Members | 100% | 2023-04-12 | 2023-05-24
| Company Logo | Angela E. Corpuz | 100% | 2023-04-12 | 2023-04-12
| Application Logo | Angela E. Corpuz | 100% | 2023-04-25 | 2023-05-22
| User Interface Layout Design | All Members | 100% | 2023-04-25 | 2023-05-24
| PROCESS | All Members | 100% | 2023-04-11 | 2023-05-24
| Unified Modelling Language | Mary Gwen G. Susa | 100% | 2023-05-22 | 2023-05-24
| Flowchart | Mary Gwen G. Susa | 100% | 2023-04-11 | 2023-05-17
Sample phase title block | PRE-DEVELOPMENT STAGE
| RESEARCH | All Members | 100% | 2023-04-13 | 2023-04-18 | 6
| Research about Basic Knowledge on Programming Tools to be Used | All Members | 100% | 2023-04-19 | 2023-04-23 | 5
| Research about References Related to Coding of the Application | All Members | 100% | 2023-04-24 | 2023-04-29 | 6
| Research about Ways on How to Monetize a Mobile Application |  | 100% | 2023-05-09 | 2023-05-15
| Research about Ways to Test an Application Before Launching | All Members | 100% | 2023-05-09 | 2023-05-15
| DOCUMENTATION |  | 100% | 2023-05-15 | 2023-05-20
| Initial Project Charter | Mary Gwen G. Susa | 100% | 2023-05-20 | 2023-05-24
Sample phase title block | Development Stage
| LOG IN |  | 100% | 2023-06-02 | 2023-06-10 | 9
| Email in Database Look Up | Mary Gwen G. Susa | 100% | 2023-06-10 | 2023-06-16 | 7
| Password in Database Matching Email Look Up | Mary Gwen G. Susa | 100% | 2023-06-16 | 2023-06-20 | 5
| Input Validation Notice | Susa, Lasco | 100% | 2023-06-20 | 2023-06-22 | 3
| Google Account Utilization | Susa, Lasco | 100% | 2023-06-22 | 2023-06-25 | 4
| SIGN UP | Susa, Lasco, Corpuz | 100% | 2023-06-25 | 2023-06-28 | 4
| Email Validation | Mary Gwen G. Susa | 100% | 2023-06-28 | 2023-06-30 | 3
| Input Validation Notice | Mary Gwen G. Susa | 100% | 2023-06-30 | 2023-07-02 | 3
| Password Strength Test | Mary Gwen G. Susa | 100% | 2023-07-02 | 2023-07-04 | 3
| Password Requirement Notice | Mary Gwen G. Susa | 100% | 2023-07-04 | 2023-07-05 | 2
| Password Matching (Backend) | Mary Gwen G. Susa | 100% | 2023-07-05 | 2023-07-08 | 4
| Password Matching (Frontend) | Mary Gwen G. Susa | 100% | 2023-07-05 | 2023-07-06 | 2
| Google Account Utilization | Susa, Lasco | 100% | 2023-07-08 | 2023-07-09 | 2
| Terms and Conditions (Frontend) | Rex-Imman H. Robles | 100% | 2023-07-09 | 2023-07-09 | 1
| Terms and Conditions (Backend) |  |  | date | date | #VALUE!
| Integration of the Frontend and Backend of the Application |  | 100% | 2023-07-09 | 2023-07-10 | 2
| HOME/FEED PAGE |  | 100% | 2023-07-10 | 2023-07-12 | 3
| Profile Button | Angela E. Corpuz | 100% | 2023-07-12 | 2023-07-12 | 1
| Pet Adoption Profile Cards | Mary Gwen G. Susa | 100% | 2023-07-12 | 2023-07-13 | 2
| Brief Animal Data Display | Mary Gwen G. Susa | 100% | 2023-07-13 | 2023-07-14 | 2
| Swiping Left |  |  | date | date | #VALUE!
| Swiping Right |  |  | date | date | #VALUE!
| Integration of the Frontend and Backend of the Application | Angela E. Corpuz | 100% | 2023-07-14 | 2023-07-14 | 1
| PROFILE PAGE | Angela E. Corpuz, Ivonne Glynn P. Lasco, Mary Gwen G. Susa | 100% | 2023-07-14 | 2023-07-15 | 2
| Home/Feed Button | Angela E. Corpuz | 100% | 2023-07-15 | 2023-07-16 | 2
| Settings Button | Ivonne Glynn P. Lasco | 100% | 2023-07-16 | 2023-07-17 | 2
| Basic Data Display | Mary Gwen G. Susa | 100% | 2023-07-17 | 2023-07-19 | 3
| Animal Adoption Profile Creation Button | Angela E. Corpuz | 100% | 2023-07-19 | 2023-07-21 | 3
| Delete Animal Adoption Profile | Susa, Lasco | 100% | 2023-07-21 | 2023-07-21
Edit Animal Adoption Profile
| Action Confirmation | Lasco, Corpuz | 100% | 2023-07-22 | 2002-07-22
| Integration of the Frontend and Backend of the Application | Susa, Corpuz | 100% | 2023-07-22 | 2023-07-22 | 1
2 | PET ADOPTION PROFILES | Corpuz, Susa | 100% | 2023-07-22 | 2023-07-23 | 2
| Complete Animal Data Display | Corpuz, Susa | 100% | 2023-07-23 | 2023-07-24 | 2
| Integration of the Frontend and Backend of the Application | Corpuz, Susa | 100% | 2023-07-24 | 2023-07-24 | 1
| ANIMAL ADOPTION PROFILE CREATION | Corpuz, Susa, Lasco | 100% | 2023-07-24 | 2023-07-25 | 2
| Camera and Photos Access Permission | Susa, Lasco | 100% | 2023-07-25 | 2023-07-25
| Pictures Upload Function | Mary Gwen G. Susa | 100% | 2023-07-25 | 2023-07-25 | 1
| Data Input Function (Breed, Medical Conditions. etc.) | Mary Gwen G. Susa | 100% | 2023-07-25 | 2023-07-26 | 2
| Action Confirmation | Lasco, Corpuz | 100% | 2023-07-26 | 2023-07-26
| Integration of the Frontend and Backend of the Application | Corpuz | 100% | 2023-07-26 | 2023-07-26 | 1
| SETTINGS | Corpuz, Susa, Lasco | 100% | 2023-07-26 | 2023-07-27 | 2
| Profile Tab | Corpuz, Susa | 100% | 2023-07-27 | 2023-07-27 | 1
| Edit User Name Display | Susa | 100% | 2023-07-27 | 2023-07-27 | 1
| Camera and Photos Access Permission | Susa, Lasco | 100% | 2023-07-27 | 2023-07-28
| Profile Picture Setup/Upload Feature | Mary Gwen G. Susa | 100% | 2023-07-28 | 2023-07-28 | 1
Actions Confirmation
| Integration of the Frontend and Backend of the Application | Corpuz | 100% | 2023-07-28 | 2023-07-29 | 2
Account Tab
Delete Account
| Log out Account | Ivonne Glynn P. Lasco | 100% | 2023-07-30 | 2023-07-30 | 1
| Actions Confirmation | Lasco, Corpuz | 100% | 2023-07-30 | 2023-07-30
| Integration of the Frontend and Backend of the Application | Corpuz, Susa, Lasco | 100% | 2023-07-30 | 2023-07-30 | 1
| Security and Privacy Frontend |  |  | date | date | #VALUE!
| Email in Database Look Up |  |  | date | date | #VALUE!
| Password in Database Matching Email Look Up |  |  | date | date | #VALUE!
| Password Strength Test |  |  | date | date | #VALUE!
| Password Matching |  |  | date | date | #VALUE!
Password Requirement Notice
Email Code Validation
Automated Email Code
Reset Password Feature
Actions Confirmation
| Integration of the Frontend and Backend of the Application |  |  | date | date | #VALUE!
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | QUALITY ASSURANCE
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | DEBUGGING | Name
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Storing User Data on the Database | All Members | 100% | 2023-06-10 | 2023-06-13 | 4
| Accessing User Data from the Database | All Members | 100% | 2023-06-13 | 2023-06-15 | 3
| Database Input Validations | All Members | 100% | 2023-06-15 | 2023-06-18 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Reset Password Feature
| Adding Animal Data on the Database | All Members | 100% | 2023-06-19 | 2023-06-22 | 4
| Displaying Animal Data from the Database | All Members | 100% | 2023-06-22 | 2023-06-26 | 5
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Swiping Pet Card Profiles
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Implementing GPS for User and Animal Matching
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Bookmarking Pet Profiles
Unbookmarking Pet Profiles
| Modifiable User Data in Settings | Mary Gwen G. Susa | 100% | 2023-06-26 | 2023-06-29
| Test Cases | Rex-Imman H. Robles | 100% | 2023-06-29 | 2023-07-03 | 5
TESTING/DRY RUN
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Functional Testing | All Members | 100% | 2023-07-03 | 2023-07-08 | 6
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | UI Testing | Angela E. Corpuz | 100% | 2023-07-08 | 2023-07-10 | 3
| Installation Testing | All Members | 100% | 2023-07-10 | 2023-07-12 | 3
| Security Testing | Mary Gwen G. Susa | 100% | 2023-07-12 | 2023-07-17 | 6
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Field Testing | All Members | 100% | 2023-07-17 | 2023-07-20 | 4
| Interrupt Testing | Mary Gwen G. Susa | 100% | 2023-07-20 | 2023-07-25 | 6
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | MONETIZATION
PREPARATION
Decide Ad Formats
Research and Decide Ad Network
Integrate Ad Network's SDK
Create Ad Placements
Configure Ad Settings
Test and Optimize
Monitor Earnings
Sample phase title block | LAUNCHING AND MAINTENANCE
LAUNCHING
Promotion
Publish App on Google Play Store
APPLICATION MAINTENANCE
| Monitor Performance | All Members
| Fix Bugs | All Members
| Improve Data Security | All Members

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.